## ProjectTeam
Name | GitHub Alias
Bruno Fernandez | brunofernandez1
Marc Brünisholz | brunm1
Samuel Ackermann | samsamann
Emanuel Huser | theonlyandone
Jan Ackermann | jan75
Dario Carosella | joeggu
Simon Wälti | iSorp

## Product Backlog
ID | Story Name | Description | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1 | Write/Read wiki articles | The LMHD writes informative articles that can be read by employees. | low | 30 | 30 | 0 | open
2 | Search contact information | The LMHD searches for contact information in the web app when other parties have to be informed about the situation. | medium | 20 | 20 | 0 | open
3 | Assign workload to employees | The LMHD assigns workloads to employees depending on factors like experience, holidays and patient conditions etc. | high | 100 | 100 | 0 | open
4 | Estimate needed resources per patient | The Employee knows the patient and can therefore estimate how much resources must be assigned to the patient. | medium | 30 | 30 | 0 | open
5 | Launch application | User can start application and see main view | high | 60 | 60 | 0 | open
|  |  |  | 240 | 240

## Sprint Backlog
ID | Sprint | Name | Description | Components | Owner | Reviewer | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
5.1 | 1 | Create Tiles Main View | This main view shows tiles which lets the user access the different parts of the application | UI, Presenter | Samuel | Emanuel | high | 6 |  |  |  | 49
5.2 | 1 | Dashboard container |  | UI, Presenter | Simon |  | high | 6
5.3 | 1 | Dashboard Item "Contact View" |  | UI, Presenter | Jan |  | medium | 6
5.4 | 1 | Dashboard Item "Wiki" |  | UI, Presenter | Marc |  | medium | 6
5.5 | 1 | Dashboard Item "Planning" |  | UI, Presenter | Emanuel |  | medium | 6
5.6 | 1 | Database Setup | Initial setup on the database, create tables for main view | Database, UI | Bruno | Jan | high | 8
3.1 | 1 | Java Entities | Create Interfaces, Classes for workload view | Model, Service |  |  | medium | 6
3.2 | 1 | Create Detail View for Planning |  | UI, Presenter |  |  |  | 6
50

## BurndownChart
Sprint | Time of Record | Remaining Effort | Remaining Ressources
1 | 2015-09-15 | 200 | 200
1 | 2015-09-16 | 190 | 180